Elevate QA CONFERENCE PLANNING PLAYBOOK

Theme - AI-Led Quality Engineering — The Proof of Value

8th August 2029 | Noida | 200–300 Attendees

Prepared by – SDET Technologies

Date Prepared: April 2026

1. EXECUTIVE SUMMARY

This playbook is our end-to-end guide to organizing a one-day conference on “AI-Led Quality Engineering — The Proof of Value” in Delhi NCR. It covers every phase from initial planning through post-event follow-up, calibrated for a 200–300 attendee event within a limited budget and a 3–4 month preparation window.

The conference targets QA engineers, test leads, SDETs, engineering managers, and CTOs who are navigating the shift toward AI-augmented testing. The goal is to establish your organization as a thought leader in this space while creating genuine community value.

Key Success Metrics

- Attendance: 300+ registered, 200+ actual attendees (assume 65–70% show rate)

- Speaker Quality: 2 keynotes from recognized industry voices + 8–10 community talks

- Engagement: 80%+ attendees rate the event 4/5 or higher in post-event survey

- Pipeline: 50+ qualified leads for consulting conversations

- Content: 10+ pieces of post-event content (blogs, videos, social clips)

2. MASTER TIMELINE (16-WEEK PLAN)

Assuming a mid-August 2026 (tentative) event date, here is the week-by-week breakdown. Adjust dates if targeting a different window.

| Phase | Weeks | Key Milestones |
| --- | --- | --- |
| Phase 1: Foundation | Weeks 1–2 | Form core team (3–5 people). Finalize date, shortlist venues, open CFP, identify keynote speakers, set up event website/landing page. Keynote : Internal – Sachin External : Rahul/Sanjay/Naveen (yet to finalise) + Panellist : 4 person: |
| Phase 2: Momentum | Weeks 3–6 | Confirm venue & keynotes. Launch early-bird registration. Begin sponsor outreach. Social media campaign starts. Review first CFP submissions. |
| Phase 3: Build-Up | Weeks 7–10 | Close CFP. Finalize speaker lineup and agenda. Secure sponsors. Ramp up marketing — LinkedIn posts, community groups, email campaigns. |
| Phase 4: Pre-Event | Weeks 11–14 | Vendor confirmations (AV, catering, printing). Rehearsals with speakers. Final attendee communications. Prepare swag and collateral. |
| Phase 5: Event Week | Weeks 15–16 | Dry run at venue. Execute event day. Post-event thank-yours and survey within 48 hours. |

3. BUDGET ALLOCATION (To be decided)

We can look to offshoot at least 50% of the budget through sponsorships-

| Category | Estimated Cost | % of Budget | Notes |
| --- | --- | --- | --- |
| Venue Rental |  | 25–30% | Conference halls at hotels or co-working campuses in Noida. Negotiate half-day or full-day packages. |
| F&B (Lunch + Tea) |  | 20–25% | Buffet lunch + 2 tea breaks. ₹400–600/head for 300 attendees. |
| AV & Production |  | 10–15% | Projectors, mics, live streaming setup. Many venues include basic AV. |
| Marketing & Design |  | 8–10% | Social media ads, email tools, banners, standees, badges, flyers. |
| Speaker Expenses |  | 10–12% | Travel/accommodation for outstation keynotes. Most community speakers self-fund. |
| Swag & Printing |  | 5–7% | Branded notebooks, stickers, lanyards, name badges, certificates. |
| Platform & Tools |  | 3–5% | Event registration (Townscript/Konfhub), email tool, feedback tool. |
| Contingency |  | 5–10% | Always keep a buffer. Unexpected costs are guaranteed. |

Sponsorship Revenue Target (Optional)- At least 50% of the overall cost

This is what makes the event financially viable. See Section 9 for the full sponsorship strategy.

4. VENUE SELECTION — DELHI NCR

For a 200–300 person tech conference, prioritize venues that offer a main auditorium/hall (theatre-style seating for 250–300), at least one breakout room, a foyer/lobby for networking and sponsor booths, on-site catering, and strong Wi-Fi.

Recommended Venue Types

- Hotel Conference Centers

- Tech Park Auditoriums

- Co-Working/Event Spaces

- University Auditoriums

Venue Checklist

- Capacity: Confirm theatre-style seating for your target number + 10% buffer

- AV: Built-in projector, screen, PA system, wireless mics (at least 3)

- Internet: Dedicated Wi-Fi for 300+ concurrent devices (test this during visit)

- Power: Adequate power outlets for speaker laptops, AV gear, and charging stations

- Parking: Sufficient parking or metro accessibility (Gurgaon Rapid Metro, Delhi Metro lines)

- Catering: On-site kitchen or permission for external caterer

- Accessibility: Wheelchair access, ramps, accessible restrooms

- Branding: Permission to put up standees, banners, sponsor displays in foyer

5. THEME DEEP-DIVE & AGENDA DESIGN

The theme “AI-Led Quality Engineering — The Proof of Value” deliberately focuses on proving measurable business outcomes from AI in testing, not just tool demos. Structure the agenda around four thematic pillars:

Thematic Pillars

- Pillar 1 — The Strategic Case: Why AI in QE now? What’s the business case? ROI frameworks, executive buy-in, and maturity models.

- Pillar 2 — The Technical Foundation: AI-assisted test generation, self-healing locators, visual testing, LLM-powered test design. Hands-on proof does not slide.

- Pillar 3 — The Human Element: Reskilling QA teams, changing team structures, the evolving role of the tester, career paths in an AI-first world.

- Pillar 4 — The Proof of Value: Case studies with real metrics. Before/after numbers. Failures and what they taught. This is the heart of the conference.

Sample Agenda

| Time | Session | Format | Pillar |
| --- | --- | --- | --- |
| 09:00 – 09:30 | Registration | Open | — |
| 09:35 – 09:55 | Welcome & Opening Remarks | MC | — |
| 10:00 – 10:20 | Keynote Speaker 1 |  |  |
| 10:25 – 10:45 | Presenter 1 |  |  |
| 10:50 – 11:10 | Presenter 2 |  |  |
| 11:15 – 11:25 | Tea Break |  |  |
| 11:30 – 11:55 | Panel Discussion |  |  |
| 12:00 – 12:20 | Presenter 3 |  |  |
| 12:25 – 12:45 | Presenter 4 |  |  |
| 12:50 – 01:50 | Lunch Break |  |  |
| 02:00 – 02:20 | Keynote Speaker 2 |  |  |
| 02:25 – 02:45 | Presenter 5 |  |  |
| 02:50 – 03:10 | Presenter 6 |  |  |
| 03:15 – 03:35 | Presenter 7 |  |  |
| 03:40 – 03:55 | Tea Break |  |  |
| 04:00 – 04:20 | Presenter 8/ Keynote Speaker 3 | Sachin Sir |  |
| 04:25 – 04:45 | Presenter 9 |  |  |
| 04:50 – 05:10 | Presenter 10 |  |  |
| 05:15 – 05:30 | Awards & Closing Remarks | MC |  |
|  | Lucky Draw Game |  |  |
|  | Trophies & Certificates |  |  |
|  | The State of AI in Quality Engineering — What the Data Shows |  |  |
| 10:15 – 10:45 | Panel: Has AI Actually Reduced Testing Costs? Honest Answers from 4 Engineering Leaders | Panel (30 min) | Proof of Value |
| 10:45 – 11:00 | + Sponsor Booth Visits | Break | — |
| 11:00 – 11:30 | Talk: Building an AI Test Generation Pipeline — Architecture & Lessons from Production | CFP Talk (30 min) | Technical |
| 11:30 – 12:00 | Talk: Self-Healing Tests at Scale — Our Journey from 40% Flakiness to 5% | CFP Talk (30 min) | Proof of Value |
| 12:00 – 12:30 | Talk: Reskilling 200 Manual Testers for an AI-First World — What Worked and What Didn’t | CFP Talk (30 min) | Human |
| 12:30 – 13:30 | Lunch + Networking | Break | — |
| 13:30 – 14:15 | Keynote 2: Beyond Test Automation — AI as Your Quality Intelligence Layer | Keynote (45 min) | Strategic |
| 14:15 – 14:45 | Talk: LLM-Powered Test Case Design — A Live Demo with Real Bugs Found | CFP Talk (30 min) | Technical |
| 14:45 – 15:15 | Talk: Visual AI Testing — Catching What Pixel-Diff Misses | CFP Talk (30 min) | Technical |
| 15:15 – 15:30 | Tea Break | Break | — |
| 15:30 – 16:00 | Lightning Talks (5 speakers x 5 min): Quick Wins with AI in QE | Lightning | Mixed |
| 16:00 – 16:30 | Fireside Chat: CTO + QA Head — The Uncomfortable Truth About AI ROI in Testing | Fireside (30 min) | Proof of Value |
| 16:30 – 16:50 | Closing Keynote: What Quality Engineering Looks Like in 2028 | Keynote (20 min) | Strategic |
| 16:50 – 17:00 | Closing Remarks, Awards & Group Photo | Closing | — |
| 17:00 – 18:00 | Open Networking + Post-Event Mixer | Informal | — |

6. KEYNOTE SPEAKER STRATEGY

We need 2–3 keynotes who bring credibility, draw attendees, and set the intellectual tone. For a first event, focus on accessible, community-connected leaders rather than unattainable celebrity speakers.

Speaker Profile Targets

- Keynote 1 — The Industry Voice: VP/Director of Engineering or QA at a major product company (e.g., Flipkart, Freshworks, Zoho, Thoughtworks, Infosys). Someone who can speak to AI in QE from real organizational experience.

- Keynote 2 — The Technical Visionary: Founder/CTO of an AI testing startup or a well-known open-source contributor in the testing space. Think founders of AI-native testing tools or prolific conference speakers.

- Closing Keynote — The Provocateur: An analyst, author, or consultant who can deliver a forward-looking, opinionated take. Shorter slot (20 min), high-energy.

How to Approach Speakers

- Start outreach in Week 1. Keynotes take 4–8 weeks to confirm.

- Personalized email explaining the theme, audience profile, and why they specifically fit.

- Offer: travel + accommodation covered, prominent billing, video recording rights shared.

- Leverage LinkedIn — most India tech leaders are highly active there.

- Ask confirmed speakers to recommend others — this is your best pipeline.

- Have 2–3 backup names for each keynote slot.

7. CALL FOR PAPERS (CFP) PROCESS

The CFP is our primary mechanism for building an interesting, diverse agenda. A well-run CFP also markets your event — every person who submits becomes invested in the conference.

CFP Timeline

| Milestone | Timing | Action |
| --- | --- | --- |
| CFP Opens | Week 1 | Publish submission form. Share across LinkedIn, Twitter, testing communities, and Slack/Discord groups. |
| Active Promotion | Weeks 2–6 | Weekly reminders. Tag potential speakers directly. Ask sponsors and partners to amplify. |
| CFP Closes | Week 7 | Hard deadline. No extensions unless submissions are critically low. |
| Review & Selection | Weeks 7–8 | Review committee (3–5 people) scores all submissions blind. |
| Speaker Notification | Week 9 | Notify accepted and waitlisted speakers. Rejected speakers get a kind note + invitation to attend. |
| Agenda Published | Week 10 | Full agenda goes live. Major marketing push. |

CFP Submission Form Fields

- Talk title (max 100 characters)

- Abstract (max 300 words) — what the attendee will learn

- Talk format preference: Full talk (30 min), Lightning talk (5 min), Panel participation

- Pillar alignment: Strategic / Technical / Human / Proof of Value

- Speaker name, designation, company, LinkedIn URL

- Speaker bio (max 150 words)

- Previous speaking experience (optional, links to past talks)

- Any special requirements (AV, demo setup, etc.)

- Short Video (1-2 Min)

- Initial Draft of Presentation

Selection Criteria (Weighted)

| Criterion | Weight | What Reviewers Look For |
| --- | --- | --- |
| Relevance to Theme | 30% | Does this directly address AI-led QE and prove value? Or is it generic test automation rebranded? |
| Originality & Insight | 25% | Is this a fresh perspective? Real experience? Or a vendor pitch disguised as a talk? |
| Practical Takeaways | 25% | Will attendees leave with something actionable? Tools, frameworks, processes, code? |
| Speaker Credibility | 10% | Has the speaker done this work, or are they theorizing? Practitioners preferred. |
| Diversity & Balance | 10% | Mix of companies, seniority levels, backgrounds, and thematic pillars. |

Anti-Pitch Policy

Make it crystal clear in the CFP that vendor pitches will be rejected. Language to use: “We welcome talks from tool creators IF the talk focuses on engineering challenges and real outcomes, not product features. Pure product demos belong in the sponsor booth, not on stage.”

8. MARKETING & REGISTRATION STRATEGY

Registration Platform

Use Konfhub or Townscript — both are India-friendly, support UPI/Razorpay, and generate attendee badges. Konfhub is especially popular with Indian tech events and has a free tier for community events.

Sample Pricing Strategy

| Tier | Price | Window | Goal |
| --- | --- | --- | --- |
| Super Early Bird | ₹299–499 | Weeks 1–4 | Create initial buzz, reward your network. 50–80 tickets. |
| Early Bird | ₹699–999 | Weeks 5–8 | Main sales window. 100–150 tickets. |
| Standard | ₹1,299–1,499 | Weeks 9–14 | Full price. FOMO-driven. |
| Student | ₹199–299 | Full window | Max 50 tickets. Require valid student ID. |
| Bulk/Corporate (5+) | 15–20% discount | Full window | Corporate teams. Invoice-based. Great for lead gen. |

Marketing Channels

- LinkedIn (Primary): This is your #1 channel for the QE audience. Post 3–4 times/week: speaker announcements, CFP reminders, behind-the-scenes, polls. Personal posts from organizer accounts outperform company pages 5x.

- Testing Communities: Ministry of Testing, QA communities on Slack/Discord, Testing Tribes India, STeP-IN Forum. Don’t just drop links — engage genuinely.

- Twitter/X: Use event hashtag consistently (e.g., #AIQEConf2026 or #ProofOfValueQE). Tag speakers in announcements.

- Email Campaigns: Build a list from registration, CFP, and partner sharing. Send 6–8 emails total: launch, speaker reveals, CFP close reminder, early bird ending, final agenda, last chance.

- WhatsApp Groups: Underrated in India. If you have access to QA/testing WhatsApp groups, use them judiciously (not spammy).

- Partner Amplification: Ask sponsors, speakers, and community partners to share with their networks. Provide them ready-made posts and graphics.

Marketing Content Calendar

| Week | Content Themes |
| --- | --- |
| Weeks 1–2 | Event announcement, theme reveal, CFP launch, early bird opens |
| Weeks 3–4 | First keynote announcement, CFP promotion, “Why attend” post series |
| Weeks 5–6 | Second keynote reveal, sponsor announcements, speaker spotlight posts |
| Weeks 7–8 | CFP closing reminder, early bird ending, agenda teasers |
| Weeks 9–10 | Full agenda reveal, “Meet the speakers” series, final pricing push |
| Weeks 11–12 | Logistics info (venue, parking, schedule), attendee testimonials (if repeat event), countdowns |
| Weeks 13–14 | Last chance registration, behind-the-scenes prep, day-of info email |
| Weeks 15–16 | Live event social coverage, real-time highlights, post-event recap |

9. SPONSORSHIP STRATEGY(Optional)

Sponsorships are critical to making this event work within your budget. Target companies selling to QA/engineering teams: test automation vendors, CI/CD platforms, cloud providers, observability tools, AI/ML platforms, and staffing/consulting firms.

Sponsorship Tiers

| Tier | Price | Benefits |
| --- | --- | --- |
| Title Sponsor |  | Logo on all materials, dedicated 10-min stage slot, premium booth, 10 complimentary passes, lead list, social media mentions, banner at entrance. |
| Gold Sponsor |  | Logo placement, booth space, 5 complimentary passes, lead list, 2 social media mentions. |
| Silver Sponsor |  | Logo placement, 3 complimentary passes, shared table, 1 social media mention. |
| Community Partner | In-kind | Logo on website, social media shout-out. In return: they promote the event to their community. Target: testing meetup groups, tech media, coding bootcamps. |
| Swag/F&B Sponsor | Variable | Branded lunch, tea break, or swag item. Logo on specific touchpoint. E.g., “Lunch sponsored by [Company]”. |

Sponsor Outreach Script

Keep the initial email under 200 words. Lead with what the sponsor gets (audience of 300+ QA decision-makers), not what you need. Attach a one-page sponsor deck (PDF) with audience demographics, expected footfall, tier benefits, and past traction (if any). Follow up within 5 days. Aim to have 2–3 sponsors confirmed by Week 6.

Target Sponsor Categories

- Test automation platforms

- CI/CD and DevOps tools (e.g., GitHub, GitLab, CircleCI, Harness)

- Cloud providers (AWS, Azure, GCP — they often have community event budgets)

- AI/ML platforms and startups (especially India-based AI-in-testing startups)

- IT staffing and QA consulting firms

- Developer tools and observability companies

10. DAY-OF-EVENT LOGISTICS

Core Team Roles (Assign by Week 10)

| Role | Responsibilities |
| --- | --- |
| Event Lead | Overall coordination, decision-making, vendor management, crisis handling. |
| Stage Manager | Speaker transitions, time-keeping (strict!), AV coordination, slide deck management. |
| Registration Lead | Check-in desk, badge distribution, walk-in management, headcount tracking. |
| Sponsor Liaison | Sponsor booth setup, ensuring deliverables are met, managing sponsor requests. |
| Content & Social | Live-tweeting, photography, Instagram stories, capturing quotes for post-event content. |
| Logistics & F&B | Catering coordination, signage, seating arrangement, power/Wi-Fi troubleshooting. |
| Volunteer Coordinator | Managing 8–10 volunteers for wayfinding, mic running, crowd management. |

Event Day Checklist

- T-minus 2 hours: Team arrives. AV check, slide deck test for every speaker, Wi-Fi speed test, signage up, registration desk ready.

- T-minus 1 hour: Caterer setup confirmed. Sponsor booths ready. Photography/videography team briefed.

- T-minus 30 min: Keynote speakers mic-checked. MC/host briefed. Registration opens.

- During event: Stage manager keeps strict time (flash cards at 5 min and 1 min remaining). Social media team captures every session.

- Post last session: Group photo. Feedback QR codes at every table. Open networking facilitated (not just “people standing around”).

AV & Technology Setup

- Primary projector + backup (or venue’s built-in). Test resolution with actual slide decks.

- 3 wireless mics: 1 lapel for speaker, 1 handheld for Q&A, 1 backup.

- Speaker timer visible on stage (use a tablet or dedicated app — Stagetimer.io is free).

- Confidence monitor (screen facing the speaker) if budget allows.

- Live streaming: Use a simple setup — OBS + YouTube Live/LinkedIn Live. One dedicated person for this.

- Recording: Record all talks for post-event content. Even a phone on a tripod works if budget is tight.

- Wi-Fi: Test with 50+ device load beforehand. Have a fallback mobile hotspot for speakers.

11. ATTENDEE EXPERIENCE DESIGN

Great conferences are remembered for how they made people feel, not just what they taught. Design intentional experiences beyond just “talk → break → talk.”

Registration & Welcome

- Pre-print name badges (not handwritten). Include name, company, and role. Color-code by type: speaker, sponsor, attendee, volunteer.

- Welcome kit: badge, lanyard, printed agenda card, pen, and one high-quality swag item (branded notebook or tote bag).

- A dedicated “first-timers” table at registration for people attending their first conference — pair them with a volunteer buddy.

Networking Facilitation

- Ice-breaker activity during breakfast: e.g., “Find someone who…” bingo card with QE-themed prompts.

- Designated “networking zones” in the foyer with standing tables and conversation starter cards.

- A shared WhatsApp or Telegram group created 2 days before the event for attendees to connect.

- During lunch, assign random table topics: “AI in Mobile Testing,” “Career Growth in QE,” etc.

Engagement Touchpoints

- Live polling during panels using Slido or Mentimeter (free tiers available).

- A physical or digital “Idea Wall” where attendees post their biggest QE challenge for others to respond to.

- Best question award — incentivizes audience participation during Q&A.

- Photo booth area with conference-branded backdrop for social media sharing.

12. POST-EVENT FOLLOW-UP

The 48 hours after the event are as important as the event itself. This is where you convert attendees into community members, leads, and advocates.

Within 24 Hours

- Send thank-you email to all attendees with: feedback survey link (Google Forms), event photos album (Google Photos/Drive), promise of talk recordings “coming in 2 weeks.”

- Post highlight reel on LinkedIn — photos, 2–3 key quotes (with permission), attendance numbers.

- Send personalized thank-you notes to speakers and sponsors.

Within 1 Week

- Publish a blog post: “5 Key Takeaways from AI-Led QE Conference 2026.”

- Share individual speaker highlight clips on social media (30–60 second cuts).

- Send sponsor deliverables: attendee list (with consent), post-event report with metrics.

Within 2–3 Weeks

- Upload full talk recordings to YouTube (with speaker permission).

- Publish detailed session recaps as individual blog posts — SEO goldmine.

- Send a “Stay connected” email with links to community channels, upcoming meetups, and a hint about the next event.

Lead Generation for Your Consulting Business

This conference is ultimately a brand and pipeline investment. Capture value through:

- A free “AI Readiness Assessment” offered at your booth or in the closing remarks.

- Follow-up emails segmented by role: CTOs get strategic content, SDETs get technical guides.

- Invite engaged attendees to a post-event “AI QE Office Hours” webinar (free, value-driven).

- Use the talk recordings and blog content as ongoing lead magnets on your website.

13. RISK MITIGATION

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Low registrations | High | Start marketing early. Use early-bird pricing aggressively. Leverage personal networks. Have 100 free community passes as a last resort. |
| Speaker no-show | High | Confirm speakers 48 hrs before. Have 2 backup talks ready (your own team or a standby speaker). Lightning talks are easy to extend. |
| Venue AV failure | High | Bring your own backup projector and mic. Do a full tech rehearsal the evening before. |
| Budget overrun | Medium | Track expenses weekly in a shared sheet. Don’t commit to optional expenses until sponsorship is confirmed. |
| Low sponsor interest | Medium | Start outreach early. Have a “slim” event plan that works with zero sponsors but reduced scope. |
| Monsoon/weather issues (if Aug) | Medium | Choose a venue with covered parking and indoor-only flow. Avoid open-air spaces. |
| Wi-Fi failure | Medium | Have 2–3 mobile hotspots as backup for speaker demos. Speakers should have offline backup slides. |
| Catering issues | Low | Confirm headcount 3 days before. Order 10% extra. Have a backup caterer’s number ready. |

14. RECOMMENDED TOOLS & PLATFORMS

| Purpose | Tool | Cost |
| --- | --- | --- |
| Registration & Ticketing | Konfhub / Townscript | Free for community events, small fee for paid |
| Event Website | Notion site / Carrd / Google Sites | Free or ₹500/year |
| CFP Management | Google Forms + Google Sheets, or Sessionize | Free |
| Design (Banners, Social) | Canva Pro | ₹5,000/year or free tier |
| Email Campaigns | Mailchimp / Brevo | Free up to 500 contacts |
| Live Polling | Slido / Mentimeter | Free tier supports basic use |
| Feedback Survey | Google Forms / Typeform | Free |
| Stage Timer | Stagetimer.io | Free |
| Live Streaming | OBS Studio + YouTube Live | Free |
| Project Management | Notion / Trello | Free tier |
| Communication (Team) | WhatsApp group or Slack | Free |
| Photo Sharing | Google Photos shared album | Free |

15. GO/NO-GO DECISION CHECKLIST (WEEK 12)

At Week 12, review the following to decide if the event proceeds as planned or needs to be scaled down/postponed:

| Checkpoint | Go Threshold | Status |
| --- | --- | --- |
| Registrations | 150+ confirmed registrations | □ |
| Venue | Confirmed and contract signed | □ |
| Keynotes | At least 2 of 3 confirmed | □ |
| CFP Talks | At least 6 of 8 slots filled with quality talks | □ |
| Sponsorship (Optional) | At least ₹2L confirmed in sponsorship | □ |
| AV & Logistics | Vendor confirmed and advance paid | □ |
| Team Readiness | All core roles assigned and rehearsed | □ |
| Budget Health | Within 15% of planned budget | □ |

If 6 of 8 checkpoints are met, proceed with confidence. If fewer than 5, consider scaling to a smaller format (e.g., half-day, meetup-style) rather than cancelling outright.